## Objectives
Objectives Matrix |  | ENTER COMPANY NAME or WORKGROUP HERE
| Overall objective: | Enter primary company or project strategy here
| PROJECT |  | ACHIEVEMENT | [5 empty] | PROGRESS |  |  |  | WORKSTREAM
Dimension of Success | Enabling Strategy | Key Performance Indicator | Why accomplishing this is important | Protect or Grow | Target | Due | Forecasted | Actual | R/G/B/G | Current Status | Risks | Mitigation Plan | Category | Functional Leader | Project Leader | Key Team Members | Outside Third Party Dependencies
DIMENSION 1 | Strategy 1 | Example: Customer Satisfaction NPS Score | We must improve our contract performance to eliminate performance penalties | PROTECT | Establish resource management infrastructure to ensure on time / on scope delivery of all customer programs | 2021-03-01 | 2021-03-01 | 2021-02-27 | DONE | Internal resource allocation system released to stakeholders on Feb 28 | Bugs in time allocation algorithm | Internal hackathon and QA to identify and resolve bugs. All bugs resolved 2/1. | Operational readiness | Fred | Julie | Craig, Cheryl, Tim | Acme Co integration to billing software. Completed 12/31.
|  |  |  | GROW |  | 2021-04-05 | 2021-04-01 |  | ON TRACK |  |  |  | Sales readiness | Mario | Karina | Janelle, Curtis, Manion | None
|  |  |  | COSTS |  | 2021-06-01 | 2021-07-15 |  | OFF TRACK |  |  |  | Finance business process | Ariel | Justin | Pierre, John, Natasha | None
| Strategy 2 |  |  | PROTECT |  | 2021-07-15 | 2021-07-01 |  | NOT STARTED |  |  |  | Program management | Jenn | Shelby | Courtney, Tyson, Rajesh | A Tech Company
|  |  |  | GROW |  | 2021-05-01 | 2021-05-01 |  | ON TRACK |  |  |  |  | Tish | Xander | Chaz, Don, Stephan | None
|  |  |  | COSTS |  | 2021-05-01 | 2021-06-01 |  | OFF TRACK |  |  |  | Operational readiness | Prashan | Maya | Eva, Terrence, Zach | None
DIMENSION 2 | Strategy 3 | Example: Customer Satisfaction NPS Score | We must improve our contract performance to eliminate performance penalties | PROTECT | Establish resource management infrastructure to ensure on time / on scope delivery of all customer programs | 2021-03-01 | 2021-03-01 | 2021-02-27 | DONE | Internal resource allocation system released to stakeholders on Feb 28 | Bugs in time allocation algorithm | Internal hackathon and QA to identify and resolve bugs. All bugs resolved 2/1. | Operational readiness | Fred | Julie | Craig, Cheryl, Tim | Acme Co integration to billing software. Completed 12/31.
NOT STARTED
NOT STARTED
| Strategy 4 | [7 empty] | NOT STARTED
NOT STARTED
NOT STARTED
DIMENSION 3 | Strategy 5 | Example: Customer Satisfaction NPS Score | We must improve our contract performance to eliminate performance penalties | PROTECT | Establish resource management infrastructure to ensure on time / on scope delivery of all customer programs | 2021-03-01 | 2021-03-01 | 2021-02-27 | DONE | Internal resource allocation system released to stakeholders on Feb 28 | Bugs in time allocation algorithm | Internal hackathon and QA to identify and resolve bugs. All bugs resolved 2/1. | Operational readiness | Fred | Julie | Craig, Cheryl, Tim | Acme Co integration to billing software. Completed 12/31.
NOT STARTED
NOT STARTED
| Strategy 6 | [7 empty] | NOT STARTED
NOT STARTED
NOT STARTED
|  |  |  | PROTECT |  |  |  |  | DONE
|  |  |  | GROW |  |  |  |  | ON TRACK
|  |  |  | COSTS |  |  |  |  | OFF TRACK
NOT STARTED